Project Management Plan

For

Academic Measurement and Achievement Mentor

Based on IEEE-1058

Version 4.0

Prepared by Ekaterina Schwartz, Monica Gloudemans

Purdue University, Fort Wayne

10-14-2011

Table of Contents

1.	Overview	1

1.1.	Project Deliverables	3

1.2.	Assumptions, Dependencies, and Constraints	3

1.3.	References	4

1.4.	Definitions and Acronyms	4

1.5.	Evolution of the Plan	4

2.	Project Organization	4

2.1.	Internal Structure	5

2.2.	Roles and Responsibilities	5

3.	Managerial Process Plans	5

3.1.	Start-Up Plans	5

3.1.1	Estimation Plan	5

3.1.2	Staffing Plan	5

3.1.3	Staff Training Plan	6

3.1.4	Resource Acquisition Plan	6

3.1.5	Project Commitments	7

3.2.	Work Plan	7

3.3.	Control Plan	9

3.3.1	Data Control Plan	9

3.3.2	Requirements Control Plan	10

3.3.3	Schedule Control Plan	10

3.3.4	Budget Control Plan	10

3.3.5	Communication, Tracking, and Reporting Plan	10

3.3.6	Metrics Collection Plan	10

3.4.	Risk Management Plan	10

3.5.	Issue Resolution Plan	11

3.6.	Project Close-Out Plan	11

4.	Technical Process Plans	11

4.1.	Process Model	11

4.2.	Methods, Tools, and Techniques	12

4.3.	Configuration Management Plan	13

4.4.	Quality Assurance Plan	13

4.5.	Documentation Plan	14

4.6.	Process Improvement Plan	14

# Overview

Elevating expectations for high academic achievement and increasing student-to-teacher ratios make the need for supplemental academic achievement tools evident. The Academic Measurement and Achievement Mentor (AMAM) is a resolution to the lack of timely and iterative assessments of students’ grasp of Indiana state academic standards, the absence of readily available enrichment materials directly linked to specific standards, and the failure to engage parents in the process of the academic standards achievement. The Academic Measurement and Achievement Mentor is geared towards academically proactive parents and their students, as well as any supporters involved with students’ academic endeavors.

The goal of the Academic Measurement and Achievement Mentor project is to provide the requirements and analysis, architecture, detail design, project management scoping, and formal documentation  for the development of a web-based tool to be used to assist students of various grade levels in mastering State mandated academic standards. The AMAM project is to be developed by implementing practices of the Rational Unified Process. For the purpose of the ACS560 course, the AMAM project is to implement the Inception and Iteration phases of the Rational Unified Process only. Deliverables for this project are to include: Vision Document, Application Architecture, Software Requirements Specification, Design Structure Matrix, Risk Analysis, Class Diagrams, Data Flow Diagrams, Use-Case Diagrams, Sequence Diagrams, and Software Design Description. Table 1 identifies project tasks, schedule and task responsibility.

| Task Name | Start | Finish | Completed by |
| --- | --- | --- | --- |
| ACS560 Project | Tue 8/23/11 | Tue 12/13/11 | E Schwartz and M Gloudemans |
| Project Brainstorming | Tue 8/23/11 | Mon 8/29/11 | E Schwartz and M Gloudemans |
| Research | Tue 8/23/11 | Tue 9/20/11 | E Schwartz and M Gloudemans |
| Vision Document | Tue 8/30/11 | Tue 9/6/11 | E Schwartz and M Gloudemans |
| Application Architecture | Tue 9/6/11 | Tue 9/27/11 |  |
| v1.0 | Tue 9/6/11 | Mon 9/12/11 | M Gloudemans |
| v2.0 | Tue 9/13/11 | Mon 9/19/11 | E Schwartz and M Gloudemans |
| v3.0 | Tue 9/20/11 | Mon 9/26/11 | M Gloudemans |
| Axiomatic Design | Tue 9/13/11 | Tue 10/4/11 |  |
| FR-DP Design Matrix | Tue 9/13/11 | Tue 9/27/11 | E Schwartz |
| DP-DP Dependency Structure Matrix | Tue 9/20/11 | Tue 10/4/11 | E Schwartz |
| Software Requirements Specification | Tue 9/13/11 | Mon 10/10/11 |  |
| v1.0 | Tue 9/13/11 | Mon 9/19/11 | M Gloudemans |
| v2.0 | Tue 9/20/11 | Mon 9/26/11 | M Gloudemans |
| v3.0 | Mon 10/3/11 | Fri 10/7/11 | M Gloudemans |
| v4.0 | Sun10/23/11 | Sun10/23/11 | M Gloudemans |
| Risk Analysis FMEA | Tue 9/20/11 | Mon 10/3/11 | E Schwartz |
| Project Management Plan | Tue 9/20/11 | Tue 10/4/11 |  |
| v1.0 | Tue 9/20/11 | Mon 9/26/11 | E Schwartz |
| v2.0 | Tue 10/10/11 | Tue 10/14/11 | E Schwartz |
| v3.0 | Mon10/24/11 | Mon10/24/11 | E Schwartz |
| Gantt chart | Tue 9/20/11 | Mon 10/3/11 |  |
| v1.0 | Fri 9/23/11 | Fri 9/23/11 | M Gloudemans |
| v2.0 | Wed 9/28/11 | Wed 9/28/11 | E Schwartz |
| v3.0 | Sun 10/16/11 | Sun10/16/11 | E Schwartz |
| v4.0 | Mon10/24/11 | Mon10/24/11 | E Schwartz |
| Software Design | Tue 10/4/11 | Tue 12/13/11 |  |
| SDD | Tue 10/18/11 | Tue 11/29/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |
| Class Diagrams |  |  |  |
| v1.0 | Tue10/18/11 | 10/25/11 | M Gloudemans E Schwartz |
| Data Flow Diagram | Tue 10/11/11 | Tue 10/25/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |
| Use Case Diagrams | Tue 10/11/11 | Tue 10/25/11 |  |
| v1.0 | Tue10/18/11 | Thu10/20/11 | M Gloudemans E Schwartz |
| Activity Diagram | Tue 10/18/11 | Tue 11/1/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |
| Sequence Diagram | Tue 10/18/11 | Tue 11/1/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |
| State Chart Diagram | Tue 11/1/11 | Tue 11/15/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |
| Progress Presentation |  |  |  |
| v1.0 | Fri 9/23/11 | Tue 9/27/11 | M Gloudemans E Schwartz |
| v2.0 | Tue10/18/11 | Tue10/18/11 | M Gloudemans E Schwartz |
| v3.0 | Fri10/21/11 | Tue10/25/11 | M Gloudemans E Schwartz |
| Project Presentation | Tue 11/29/11 | Tue 12/13/11 |  |
| v1.0 | TBD | TBD | M Gloudemans E Schwartz |

Table 1 AMAM project tasks, schedule and owner task assignment.

- The objective of the AMAM project is to provide a model for the development of a web-based academic achievement application. For the purpose of the ACS560 course requirements, the model is to include Inception and Elaboration phase tools of the Rational Unified Process. The objective for the complete AMAM application is to provide timely and iterative assessments and remediation or enrichment materials to be used proactively by students and persons involved in the academic process, with the ultimate result of academic mastery of standards evidenced by improved standardized test scores. Pre-test and post-test studies are to be used to determine the effectiveness of the complete application.  In addition, Usability Testing is to be conducted to gauge the user-friendly interface among different age groups.

- The Academic Measurement and Achievement Mentor is to implement existing assessment and report-generating software, as well as a combination of software, web-links, and instructional videos for enrichment and remediation. Therefore, the research of appropriate material is a vital part of successful completion of the application. The conclusion of unavailability of appropriate software and enrichment material will require the development of such, resulting in resource, deliverables, and schedule revisions.

## Project Deliverables

| Deliverable | Template or Standard | Recipients | Delivery Date | Delivery Method | Comments |
| --- | --- | --- | --- | --- | --- |
| Vision Document | RUP | Sponsor | 09-10-2011 | Cmap | ACS560 project scope |
| Application Architecture | 3-tier architecture for web applications | Sponsor | 09-13-2011 | Cmap | ACS560 project scope |
| Software Requirement Specification | IEEE-830 template | Sponsor | 09-27-2011 | Cmap | ACS560 project scope |
| Design Structure Matrix | Axiomatic Design | Sponsor | 10/04/2011 | Cmap | ACS560 project scope |
| PMP | IEEE-1058 template | Sponsor | 10/07/2011 | Cmap | ACS560 project scope |
| Risk Analysis FMEA | ACS 560 class standard | Sponsor | 09-27-2011 | Cmap | ACS560 project scope |
| Design Matrix | Axiomatic Design | Sponsor | 10/04/2011 | Cmap | ACS560 project scope |
| Gantt Chart | ACS 560 class standard | Sponsor | 09-27-2011 | Cmap | ACS560 project scope |
| SDD | IEEE-1016 template | Sponsor | TBD | Cmap | ACS560 project scope |
| Class Diagrams | UML | Sponsor | TBD | Cmap | ACS560 project scope |
| Component Diagram | UML | Sponsor | TBD | Cmap | ACS560 project scope |
| Activity Diagrams | UML | Sponsor | TBD | Cmap | ACS560 project scope |
| Sequence Diagrams | UML | Sponsor | TBD | Cmap | ACS560 project scope |
| Use-Case Diagrams | UML | Sponsor | TBD | Cmap | ACS560 project scope |
| Project Presentation | ACS 560 class standard | Sponsor | 12/13/11 | Cmap / presentation | ACS560 project scope |
| Project Binder | ACS 560 class standard | Sponsor | 12/13/11 | In class | ACS560 project scope |
| Project CD | ACS 560 class standard | Sponsor | 12/13/11 | In class | ACS560 project scope |
| CMAP | ACS 560 class standards | Sponsor | 12/13/11 | Publicly posted Gloudemans/Schwartz CMAP for ACS560 | ACS560 project scope |

Table 2 AMAM project deliverables.

## Assumptions, Dependencies, and Constraints

The Academic Measurement and Achievement Mentor will be developed based on the following assumptions, dependencies, and constraints:

AS-1 Availability of RUP project development tools

DE-1 Availability of accurate standards assessment software

DE-2 Availability of reporting software

DE-3 Availability of current Indiana academic standards for each grade level

DE-4 Availability of browser helper plug-ins

DE-5 Availability of web browser

DE-6 Availability of persistent storage system

DE-7 Availability of database systems

DE-8 Availability of session management application

DE-9 Availability of authorization application

DE-10 Availability of authentication application

DE-11 Availability of web server

DE-12 Availability of web services to provide payment management

DE-13Availability of web services to provide accounting services

DE-14 Availability of web services to provide content management

DE-15Availability of the Internet

DE-16 User’s access to computer

CO-1 Course duration time constraint

CO-2 Extend of owners’ experience and familiarity with project development tools and software

## References

| Documents and Materials | Access |
| --- | --- |
| AMAM Vision 1.0 | http://cmapspublic.ihmc.us/rid=1JTCCBP9S-F7499N-341L/Inception%20Phase.cmap |
| AMAM Application Architecture | http://cmapspublic.ihmc.us/rid=1JTCCBP9S-F7499N-341L/Inception%20Phase.cmap |
| AMAM SRS-based on IEEE-830 | http://cmapspublic.ihmc.us/rid=1JTCCBP9S-F7499N-341L/Inception%20Phase.cmap |
| FMEA | http://cmapspublic.ihmc.us/rid=1JTCCBP9S-F7499N-341L/Inception%20Phase.cmap |
| Gantt Chart | http://cmapspublic.ihmc.us/rid=1JVXFQ725-JCK90K-1C58/GanttChartv1_0.pdf |
| IBM Rational Unified Process | http://www.ibm.com/developerworks/rational/library/content/03July/1000/1251/1251_bestpractices_TP026B.pdf |
| AMAM SDD-based on IEEE-1016 |  |
| Class Diagrams | TBD |
| Component Diagram | TBD |
| Use-Case Diagrams | TBD |
| Sequence Diagram | TBD |

Table 3 AMAM references.

## Definitions and Acronyms

The following is a list of definitions of acronyms and abbreviations.

| Acronym | Description |
| --- | --- |
| AMAM | Academic Measurement and Achievement Mentor |
| RUP | Rational Unified Process |
| SRS | Software Requirements Specification |
| FMEA | Failure Modes and Effects Analysis |
| DSM | Design Structure Matrix |
| FR | Functional Requirement |
| DP | Design Parameter |
| UML | Unified Modeling Language |
| PMP | Project Management Plan |
| SDD | Software Design Description |

Table 4 AMAM definitions and acronyms.

## Evolution of the Plan

The project management plan is to be updated upon the modification of the SRS, application architecture, FMEA, and changes in the state of dependencies and assumptions. In addition, scheduled weekly review and modification will be conducted as new documentation is introduced and sponsor input is received.

# Project Organization

The Academic Measurement and Achievement Mentor project is developed as part of the ACS560 course work requirement. As an academic project, it does not involve external entities such as customers, subcontractors, purchasing, sales, marketing, legal, finance, procurement, and support individuals or organizations.

## Internal Structure

The Academic Measurement and Achievement Mentor is a collaborative project between Monica Gloudemans and Ekaterina Schwartz. Project review and guidance is provided by Dr. Tanik, project’s sponsor.  Project work is subdivided among group members by delegating subtasks to each member; however, every output is reviewed and contributed to by each member before submission, thereby making each component of the project a collaborative component.

## Roles and Responsibilities

- The Academic Measurement and Achievement Mentor is a collaborative project. Project participants include owners Monica Gloudemans and Ekaterina Schwartz, and project sponsor, Dr. Tanik. Project owners are responsible for completing the documentation and analysis following the Rational Unified Process and as specified by the project’s sponsor.

- Dr. Tanik is responsible for monitoring the project’s progress and providing project input and guidance, as well as evaluating project performance.

- Students, parents, and students support are not identified as external stakeholders to the project within the scope of the ACS560 course requirement. Such will be required and identified for a complete AMAM project.

# Managerial Process Plans

## Start-Up Plans

### Estimation Plan

The AMAM project, within the scope of the ACS560 course work, does not incorporate a cost component. As a result, no cost estimates are conducted.

### Staffing Plan

- The Academic Measurement and Achievement Mentor project, within the scope of the ACS560 course work, is completed through the collaboration of the project’s owners, Monica Gloudemans and Ekaterina Schwartz. The collaboration period spans throughout the duration of the ACS560 course. Minimum skills required of each owner are skills acquired through the successful completion of pre-requisite course work in preparation for the ACS560 course.

- Dr. Tanik is responsible for monitoring the project’s progress, providing project input and guidance, as well as evaluating project performance. The duration of Dr. Tanik’s involvement with the project spans throughout the duration of the ACS560 course. Dr. Tanik possesses experience as a project sponsor and software engineering instructor, among others.

- Table 5 identifies task, duration, and assigned owner (s).

| Task Name | Duration | Assigned to |
| --- | --- | --- |
| Project Brainstorming | 5 days | E Schwartz and M Gloudemans |
| Research | 21 days | E Schwartz and M Gloudemans |
| Vision Document | 6 days | E Schwartz and M Gloudemans |
| Application Architecture v1.0 | 5 days | M Gloudemans |
| Application Architecture v2.0 | 5 days | E Schwartz and M Gloudemans |
| Application Architecture v3.0 | 5 days | M Gloudemans |
| FR-DP Design Matrix | 11 days | E Schwartz |
| DP-DP Dependency Structure Matrix | 11 days | E Schwartz |
| SRS v1.0 | 5 days | M Gloudemans |
| SRS v2.0 | 5 days | M Gloudemans |
| SRS v3.0 | 5 days | M Gloudemans |
| SRS v4.0 | 1 day | M Gloudemans |
| Risk Analysis FMEA | 10 days | E Schwartz |
| PMP v1.0 | 5 days | E Schwartz |
| PMP v2.0 | 6 days | E Schwartz |
| PMP v3.0 | 1day | E Schwartz |
| Gantt chart v1.0 | 1 day | M Gloudemans |
| Gantt chart v2.0 | 1 day | E Schwartz |
| Gantt chart v3.0 | 1 day | E Schwartz |
| Gantt chart v4.0 | 1day | E Schwartz and M Gloudemans |
| SDD | 31 days | E Schwartz and M Gloudemans |
| Class Diagrams v1.0 | 5 days | E Schwartz and M Gloudemans |
| Data Flow Diagram v1.0 | 5 days | E Schwartz and M Gloudemans |
| Use Case Diagrams v1.0 | 5 days | E Schwartz and M Gloudemans |
| Activity Diagram v1.0 | 5 days | E Schwartz and M Gloudemans |
| Sequence Diagram v1.0 | 5 days | E Schwartz and M Gloudemans |
| State Chart Diagram v1.0 | 5 days | E Schwartz and M Gloudemans |
| Progress Presentation | 3 days | E Schwartz and M Gloudemans |
| Project Presentation v1.0 | 5 days | E Schwartz and M Gloudemans |

Table 5 Tasks, duration, and assigned owner.

### Staff Training Plan

Training for the completion of project outcomes is provided to project’s owners by Dr. Tanik in the form of lectures on a weekly basis. Additional training is obtained through weekly reading and project research as assigned by Dr. Tanik or individually selected by owners based on their experience.

### Resource Acquisition Plan

Development resources necessary for the completion of the project within the scope of the ACS560 course requirements are:

- Computer for each owner

- Internet connection

- Microsoft Office Word

- Microsoft  Project

- Microsoft Visio

- Microsoft PowerPoint

- Cmap Tools

- Acclaro DFSS

- Document Templates

- Standards

- RUP White Paper

No acquisition steps for owners’ computer and internet connection are necessary.

The Microsoft software resources listed above are acquired through the university’s MSDN Academic Alliance WebStore. Acclaro DFSS is downloaded through the University Licensing System. Templates, standards, and references are provided by project’s sponsor, Dr. Tanik.

Product resources include a paper copy and a CD copy of the project’s deliverables.

### Project Commitments

Table 6 shows project commitments, participants, commitment frequency and a brief explanation.

| Commitment | Made By | Made To | Due Date | Comments |
| --- | --- | --- | --- | --- |
| Weekly sponsor updates | E Schwartz M Gloudemans | Dr. Tanik | Weekly | Weekly emails with link to updated Cmap |
| Meet sponsor deadlines | E Schwartz M Gloudemans | Dr. Tanik | Weekly | Complete requested assignments by sponsors deadline |
| Review before Cmap update | E Schwartz M Gloudemans | M Gloudemans E Schwartz | Frequent | Make each other’s work available for review and input before Cmap update |
| Timely feedback | E Schwartz M Gloudemans | M Gloudemans E Schwartz | Frequent | Provide timely feedback on work progress |

Work Plan

Table 6 Project Commitments.

Table 7 depicts project phase, activities, outcomes and predecessor tasks.

| Phase | Activities | Outcomes | Predecessor tasks |
| --- | --- | --- | --- |
| Inception | - Project Brainstorming - Obtain vision document template - Complete v1.0 | Vision document v1.0 | - Narrow down project topic |
|  | - Determine type of application - Research architectures of same type - Download Microsoft Visio and template - Complete v1.0 - Revise to v2.0 - Revise to v3.0 | Preliminary Application Architecture | - Vision document v1.0 |
|  | - Determine FRs - Determine DPs - Enter in Acclaro tool - Create FR-DP matrix - Enter and Dependencies | Preliminary FR-DP Matrix | - Vision document v1.0 - Preliminary SRS - Application Architecture |
|  | - Create DP-DP matrix - Enter DP-DP dependencies | Preliminary DP-DP Dependency Structure Matrix | - Preliminary FR-DP matrix |
|  | - Determine external interfaces - Determine functions - Determine performance requirements - Determine logical database requirements - Determine design constraints - Determine software system attributes - Outline change management process | Preliminary Software Requirements Specification | - Vision document v1.0 - Application Architecture |
|  | - Determine potential failures - List potential failures in Acclaro tool - Determine risk factors | Preliminary Risk Analysis FMEA | - Vision Document - Application Architecture |
|  | - Compile completed work for presentation | Progress Presentation | - All work completed to date of presentation |
| Elaboration | - Determine Data Flow - Create diagram with Microsoft Visio | Data Flow Diagram v1.0 | - Preliminary SRS - Preliminary SDD v1.0 |
|  | - Determine Classes - Determine attributes - Determine procedures - Determine relationships - Create diagram with Microsoft Visio | Class Diagrams v1.0 | - Preliminary SRS - Preliminary SDD v1.0 |
|  | - List actors - List goals - List dependencies - Create diagram with Microsoft Visio | Use Case Diagram v1.0 | - Vision document v1.0 - Preliminary SRS - Application Architecture - Preliminary SDD v1.0 |
|  | - List step-by step workflow - Create diagram with Microsoft Visio | Activity Diagram v1.0 | - Vision document v1.0 - Preliminary SRS - Application Architecture - Preliminary SDD v1.0 |
|  | - Determine process interaction - Create diagram with Microsoft Visio | Sequence Diagram v1.0 | - Vision document v1.0 - Preliminary SRS - Application Architecture - Preliminary SDD v1.0 |
|  | - Determine states, events [guards], actions - Create diagram with Microsoft Visio | State Chart Diagram v1.0 | - Vision document v1.0 - Preliminary SRS - Application Architecture - Preliminary SDD v1.0 |
|  | - Read standard IEEE1016 - Determine design views, attributes, entities, relationships and constraints - Implement SDD IEEE standard template | Preliminary Software Design Description v1.0 | - Vision document v1.0 - Application Architecture - Preliminary SRS |
|  | - Compile current project outputs into presentation | Progress Presentation v1.0 | - All current project outputs |
|  | - Compile project outputs Into presentation slides | Project Presentation v1.0 | - All project outputs |

Table 7 AMAM Work Plan.

## Control Plan

### Data Control Plan

Project deliverables are uploaded to project’s Cmap weekly. A copy of each delivered document is stored locally by each project owner. Document templates are provided by project sponsor, Dr. Tanik through University’s Blackboard. Non-deliverable documents such as research papers, additional reading, templates, and project’s Cmap are stored locally by each project owner.

### Requirements Control Plan

Within the scope of the ACS560 course, any changes in the requirements are initiated by project’s owners or project’s sponsor. Such are reflected in a new version of SRS, Acclaro tool files, and the PMP. In addition, the project’s Gantt chart is updated to reflect the changes.

### Schedule Control Plan

Project’s progress is tracked and monitored with the implementation of a Gantt chart, Microsoft Project.  Weekly progress reviews with project’s sponsor provide additional progress measurement and opportunity for suggestions for corrective actions. Gantt chart is modified and workload is distributed among project owners based on sponsor input.

### Budget Control Plan

The Academic Measurement and Achievement Mentor project, within the scope of the ACS560 course, does not necessitate a budget control plan.

### Communication, Tracking, and Reporting Plan

| Type of Communication | Communication Schedule | Typical Communication Mechanism | Who Initiates | Recipient |
| --- | --- | --- | --- | --- |
| Schedule and Effort Tracking Report | as needed | email | Project owners | Project owners |
| Status Report | Every Tuesday | Class meeting | Project sponsor | Project owners |
| Project Review | monthly | presentation | Project sponsor | Project owners ACS560 class |
| Requirement Changes | as changes are approved | email and class meeting | Project sponsor Project owners | Project owners |
| Project Review | at project completion | presentation | Project sponsor | Project sponsor Project owners ACS560 class |

Table 8 Communication, tracking, and reporting plan.

### Metrics Collection Plan

The project’s Gantt chart contains project tasks and deliverables, baseline start and finish dates, actual start and finish dates, and percentage completed. Such are indicators of performance in terms of meeting requested deadlines and project progress. Project’s Gantt chart is updated weekly after sponsor input is received and tasks are assigned.

Project metrics about the content of deliverables are determined and retained by project sponsor, Dr. Tanik.

## Risk Management Plan

Failure Mode and Effects Analysis implemented with the Acclaro tool is used to identify, analyze, and prioritize risks associated with the Academic Measurement and Achievement Mentor application.

## Issue Resolution Plan

Any problems, issues, and action items that arise during the completion of the project are communicated through email or during class meeting. Any change requirements supplied by the project sponsor are recorded by each owner, and the owner responsible for a revision is assigned. Owner assignment gears towards achieving equal workload and is also based on previous tasks completed. The revised document is emailed between owners for review and input. This process is repeated until all revisions are accepted and a new document version is ready for submission. Changes that do not necessitate a document revision are also divided among project’s owners. The completion of change requests is followed up with informative emails among project owners.

Decision making between project owners is dynamic and based on the particular issue at hand. Factors for determining the decision maker for a particular issue are owner’s experience and research in the area of discussion.

## Project Close-Out Plan

The close-out of the Academic Measurement and Achievement Mentor project, within the scope of the ACS560 course, consists of a project presentation and compilation of project binder and project copy CD. The presentation is conducted by both owners and includes the latest version of each project outcome.

# Technical Process Plans

## Process Model

The Academic Measurement and Achievement Mentor is developed following the Rational Unified Process (RUP). The Rational Unified Process provides guidelines, templates and tool mentors for the following best practices:

- Develop software iteratively

- Manage requirements

- Use component-based architectures

- Visually model software

- Verify software quality

- Control changes to software

RUP is described in two dimensions:

- Horizontal axis- representing the time and dynamic aspect of the process, expressed in terms of cycles, phases, iterations, and milestones

- Vertical axis- representing the static aspect of the process, in terms of activities, artifacts, worker and workflows

RUP divides one development cycle in four consecutive phases as follows:

- Inception phase

- Elaboration phase

- Construction phase

- Transition phase

Each phase is concluded with a milestone.

The outcome of RUPs inception phase is:

- A vision document: a general vision of the core project’s requirements, key features, and main constraints.

- An initial use-case model

- An initial business case

- An initial risk assessment

- A project plan

- A business model

- One or several prototypes

Evaluation criteria for the inception phase are:

- Stakeholder concurrence on scope definition and cost/schedule estimates.

- Requirements understanding as evidenced by the fidelity of the primary use cases.

- Credibility of the cost/schedule estimates, priorities, risks, and development process.

- Depth and breadth of any architectural prototype that was developed.

- Actual expenditures versus planned expenditures.

The outcome of RUPs elaboration phase is:

- A use-case model.

- Supplementary requirements capturing the non functional requirements and any requirements that are not associated with specific use-case.

- A software architecture description.

- An executable architectural prototype.

- A revised risk list and a revised business case.

- A development plan for the overall project.

- An update development case specifying the process to be used.

- A preliminary user manual

Evaluation criteria for the elaboration phase are:

- Is the vision of the product stable?

- Is the architecture stable?

- Does the executable demonstration show that the major risk elements have been addressed and credibly resolved?

- Is the plan for the construction phase sufficiently detailed and accurate? Is it backed up with a credible basis of estimates?

- Do all stakeholders agree that the current vision can be achieved if the current plan is executed to develop the complete system, in the context of the current architecture?

- Is the actual resource expenditure versus planned expenditure acceptable?

The construction and transition phases of the Rational Unified Process are not applied to this project within the scope of the ACS560 course work, and their discussion will therefore be omitted.

Not every outcome of RUP’s inception and elaboration phases is developed for this project due to the time constraint of the course.

## Methods, Tools, and Techniques

- The outcomes of the inception and elaboration phases of the Academic Measurement and Achievement Mentor project are produced on standard PCs with Operating Systems compatible with the following software:

- Microsoft Office Word- Vision document, SRS, top-level FR-DPs, SDD

- Microsoft  Project- Gantt chart

- Microsoft Visio- Data Flow diagram, Use-Case diagram, Activity diagram, Sequence diagram, State chart, Application Architecture

- Microsoft PowerPoint- Progress presentation, Close-out presentation

- Cmap Tools- Storage and management of project outcomes

- Acclaro DFSS- FMEA, DSM

The following standards, languages, theories, and templates are implemented within the project:

- The Axiomatic Design Theory-mapping of functional requirements and design parameters

- IEEE Recommended Practice for Software Requirements-SRS

- SRS Software Requirement template- adapted from the IEEE Guide to Software Requirements Specifications (Std 830-1993)

- SDD Software Design Description template- (Std 1016-2009)

- Three-Tier web-based application approach- Application Architecture

- RUP Vision document template- Vision document

- UML- Data flow diagram, use-case diagram, activity diagram, sequence diagram, state chart diagram

- Quality assurance practices are not developed within the scope of the ACS560 course work.

## Configuration Management Plan

Baselines are established by project’s sponsor. Any changes requested by the project sponsor are recorded by each owner, and the owner responsible for completing changes is assigned. The completion of changes is followed up with informative emails among project owners.

## Quality Assurance Plan

To assure project quality, each of the project’s outcomes is reviewed and contributed to by both project owners. Further, project sponsor is notified by email with link to project’s Cmap for review and input. Progress presentation provides additional peer review and input to project’s deliverables.

## Documentation Plan

| Document | Template or Standard | Created By | Reviewed By | Target Date | Distribution |
| --- | --- | --- | --- | --- | --- |
| Vision document | RUP | M Gloudemans E Schwartz | Dr. Tanik | 09/26/2011 | Cmap |
| Application Architecture | 3-tier web-based pattern | M Gloudemans | Dr. Tanik | 9/26/2011 | Cmap |
| FR-DP Design Matrix | Axiomatic Design | E Schwartz | Dr. Tanik | 9/27/2011 | Cmap |
| DP-DP Dependency Structure Matrix | Axiomatic Design | E Schwartz | Dr. Tanik | 10/04/2011 | Cmap |
| SRS | IEEE-830 template | M Gloudemans | Dr. Tanik | 10/7/2011 | Cmap |
| SDD | IEEE-1016 template | M Gloudemans E Schwartz | Dr. Tanik | 11/29/2011 | Cmap |
| PMP | IEEE-1058 template | M Gloudemans E Schwartz | Dr. Tanik | 10/7/2011 | Cmap |
| Gantt Chart | N/A | M Gloudemans E Schwartz | Dr. Tanik | 9/28/2011 | Cmap |
| Class Diagrams | UML | M Gloudemans E Schwartz | Dr. Tanik | 11/01/11 | Cmap |
| Component Diagram | UML | M Gloudemans E Schwartz | Dr. Tanik | 11/08/11 | Cmap |
| Use-case Diagrams | UML | M Gloudemans E Schwartz | Dr. Tanik | 11/01/2011 | Cmap |
| Activity Diagram | UML | M Gloudemans E Schwartz | Dr. Tanik | 11/15/2011 | Cmap |
| Sequence Diagram | UML | M Gloudemans E Schwartz | Dr. Tanik | 11/15/2011 | Cmap |
| Progress Presentation | N/A | M Gloudemans E Schwartz | Dr. Tanik | 9/27/2011 | Cmap |
| Project Presentation | N/A | M Gloudemans E Schwartz | Dr. Tanik | 12/13/2011 | Cmap |

Table 9 AMAM Document plan.

## Process Improvement Plan

A Process Improvement Plan is not developed for Academic Measurement and Achievement Mentor within the scope of the ACS560 course.

Revision History

| Name | Date | Reason for Changes | Version |
| --- | --- | --- | --- |
| Ekaterina Schwartz Monica Gloudemans | 09/22/11 | To complete document’s Overview and Project Organization sections. | 1.0 |
| Ekaterina Schwartz Monica Gloudemans | 10/14/11 | To complete document’s Managerial Process Plans and Technical Process Plans sections | 2.0 |
| Ekaterina Schwartz Monica Gloudemans | 10/24/11 | To implement sponsor’s input and to update tables 1, 2, 3, 5, 7, 9 | 3.0 |
| Ekaterina Schwartz Monica Gloudemans | 11/09/11 | To update deliverables chart | 4.0 |