## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 1/25/2012 - 2/1/2012
Group Member | Role | Progress Description | Time Alloted (hrs)
Matthew Rasler | Project Manager | Group Meeting Preperation | 3 hours
| Web Interface Programmer | Designed GUI Application (in QT) to verify software capability of application to web communication. | 10 hours
|  | Developed Psuedo-code to assist Mark in PHP development | 1 hour
|  | Set up database and server access, communicated instructions for use, to enable Mark to develop PHP component for Web Service. | 1 hour
| Student | PMBOK 2-3 | 2 hours
Andrew Habegger | Assistant Project Manager | Group Meeting Preperation | 1 hours
| Software Developer | Modified firmware to use SETOUT instead of UART (propagation delay reduced from 5s to 0.5s) | 2 hours
| Hardware Developer | Engineered RS-232 TX to RS-485 TX cable | 1 hour
| Student | PMBOK 2-3 | 2 hours
Eun Young Shin | Group Member | Modifiying Group Cmap | 3 hours
| Student | Read PMBOK 2-3 | 4 hours
|  | Summarize PMBOK 2-3 | 2 hours
Sunyoung Park | Group Member | Read PMBOK chapter5-6 | 2 hours
| Student | Summarize PMBOK chapter5-6 | 2 hours
|  | Learning Orchard CMS | 3 hours
Notes from Group Meeting 1/25/12
Post these notes on the bottom of the weekly progress report.
TASKS FOR THIS SEMESTER:
-Primary Application: Software
--Refine Jam Detection Logic. We've abandoned RANSAC and are now going with an algorithm supplied by the client.(2/1/12)
--The GUI needs refined.(2/1/12)
---Configuration tab radio buttons need replaced with stylized list view.(2/1/12)
---QTimer needs replaced with event-driven signals/slots. Polling is making the GUI lag. (2/1/12)
--Needs to serialize egg counts.(2/1/12)
--Refine Logging. Add error descriptions for serial communication (e.g. Time outs; bad responses (too little, too much); application start time, application end time (for opening and closing the app))
--Hamming codes to detect/correct communication errors.
-Primary Application: Firmware
--Write pbasic program to use dedicated serout/serin pins to bypass UART.
--Hamming code receiving/transmission
-Hardware
--Ruled out 422 line. Using 485.
--Test 486 through a dedicated serout and serin pin to bypass the UART.
--Install ADAM serial converters.
-web Development 1: Business Site
--To be developed further.
--Matt and Mark researching application-to-web page connectivity.
-Web Development 2: Group Site
--This will be a web version of our CMap, but more visually appealing.
--Incorporates a Content Management Solution (CMS): Orchard.
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler
Mark Parker
Andrew Habegger
Eun Young Shin
Sunyoung Park