## Sheet1
EARL: Egg Alert and Real-Time Logistics
Weekly Progress Status 4/18/2012 - 4/25/2012
Group Member | Role | Progress Description | Time Alloted (hrs) |  | PM Grade | Self Grade | Explanation Needed
Matthew Rasler | Project Manager | Revised PMP, added requested columns | 3
|  | Started compiling portfolio | 3
|  | Web Development for EarlWebBiz | 11
|  | Total: | 17 |  | 10 | 10
Eun Young Shin | CMap Manager | Update Files on CMap | 3
|  | Modifying CMap | 2
|  | Total: | 5 |  | 10 | 10
Sunyoung Park | Gropu Web Page | Update Group Web page | 2
|  | Project Portfolio | 2
|  | Total: | 4 |  | 10 | 10
Andrew Habegger | Software Developer | Fixed a bug in jam detection | 4
|  | Project portfolio | 1
|  | Total: | 5 |  | 10 | 10
Mark Parker | Design Engineer | Format change for DM | 1
|  | Format change for DSM | 2
|  | Exam 2 | 9
|  | Total: | 12 |  | 10 | 10
Notes from Group Meeting 4/25/2012
Finalize project portfolio components
Collect PMBOK and SWEBOKS
TASKS FOR THIS WEEK:
Group Member | Task |  |  | Completion Date
Matthew Rasler | Finish project portfolio compilation
Presentation
CMAP to CD
WebPage to CD
Andrew Habegger | Finis projcet portfolio
Presentation
Source code to CD
Mark Parker | Build new portfolio with modified componenents
Finish SDD
Eun Young Shin | Presentation prep
cmap finalize
Sunyoung Park | Presentation prep
finalize webpage